## List
TelnyxLib |  |  | Estimated time | Query
We need to implement Telnyx inteface as class libarary (it will be used in other projects)
API needed to implement
| Numbers API | Number Searching Endpoints | 4
|  | Supported Countries Endpoints | 3
| Messaging API | Messaging Profiles Endpoints | 3
|  | Messaging Settings Endpoints | 6
|  | Messages Endpoints | 5
|  | Receiving Webhooks (It should be in API to check delivery status) | 12
| Account API | Addresses Endpoints | 4
Reports API
|  | MDR Reports Endpoints | 6
|  | MDR Usage Reports Endpoints | 5
Monthly charges Endpoints
| Caller ID API | Get Caller ID Endpoints | 4
| Auth API | Actions Endpoints | 5
|  | Resource Groups Endpoints | 3
|  | Permission Groups Endpoints | 4
|  | API Keys Endpoints | 3
|  | Access Tokens Endpoints | 4
Notes | TelnyxLib should be in separated repository and use it as submodule in iMarketing repository
Client Side |  |  | Estimated time
Page Name | Actions
Login Page
| Login | Login, forgot password | 6
Main Screen |  | As I see it now we - the main screen may have 3-4 tabs | 3
TAB-2 Data Import | Import from excel | open excel file of predefined sructure . For example 1st sheet , column A - Full name, column B - phone number, column C (optional) - company, column D (optional) - position, column E (optional) - notes | 4
| Add new, Edit existing, Delete contact |  | 6
| Save imported data to the db |  | 5
|  | Validation for data? |  | Not Clear
|  | clients table should has "Business Type" and will like "Farming" , "Distrubors" , "Carriers" …. |  | Not Clear
These types should be in seperated table to allow add new types.
TAB - 1 Contacts | Load data from DB into grid
|  | loads all the contacts that were imported previously. | 4
|  | Sorting and filters based "Business type" |  | not clear
TAB-3 Templates | Message templates | Add, edit template | 3
|  | Template will look like " Hey, {#ContactName}, we have new exclusive deal for you" . {#ContactName} will be replaced with name of the contact OR simple text without placeholders for contact's data | 3
TAB - 1 Contacts | Send SMS to selected contacts
|  | column with checkbox to select contacts | 3
|  | column with Date of previous SMS message sent to this contact | 4
|  | select template from list or enter free text | 4
|  | validation of select contacts against phone number is US or CA, or not null; name is not null or empty | 4
|  | Ask for confiramation | 4
|  | Calculate number of SMS messages | 5
TAB - 1 Contacts | Check delivery status
|  | Check delivery status and update database with most recent data | 6
| f. Tracking clients whom message has been sent or not. | it should be a relation between sent message and clients. I think it can be and intermedia table between sentMessages and clients. | 10
TAB - 4 Admin | Show only for user with Admin role | It should be used to add/update users and send activation email to them, activate/deactive | 8
Server Side |  |  | Estimated time
API Methods
| Login(name, password) | We need to implement two factor factor authentication (email & password and sms code verification) | 6
| Logout(token) | Reset pass and froget pass should be included | 4
| AddNewUser(User) | It should be authorized only for admin | 8
| activateUser(boolean active) | It should be authorized only for admin | 5
| AddContactType |  | 4
| DeleteContactType |  | 4
| UpsertContacts( contact[] ) |  | 3
| DeleteContacts( contact[] ) |  | 2
| GetAllContacts() |  | 4
| UpsertTemplate( template ) |  | 3
| DeleteTemplate( templateId ) |  | 3
| GetAllTemplates() |  | 4
| SendSMS( contactId[], messageText) | Call telnyx API to send SMS messages | 8
| CheckDeliveryStatus | Call telnyx API to get the status of messages. | 6
For this point you can check Messaging Receiving Webhooks
Grand total